## Slide 1: REVIEW AND ASSESSMENT PROCESS OF SITE AUTHORIZATION APPLICATION
AHMED DANJUMA N.
DEPARTMENT OF AUTHORIZATION AND ENFORCEMENT

## Slide 2: CONTENT
Objective of Review & Assessment
Development and Use of procedures for Review and Assessment
Review Schedule and Planning
Oversight of Review and Assessment Process
Implementation of Review and Assessment Process
Documents Generated By Review and Assessment
2

## Slide 3: OBJECTIVES OF REVIEW & ASSESSMENT
    Determine whether the site complies with the Safety Objective, Principles and Criteria
    To evaluate with reference to regulatory requirements as defined by national regulations, regulatory guides, IAEA safety standards, industrial codes etc.
    Ensure that the Site is within the safe envelop

## Slide 4: GUIDANCE FOR CONDUCT OF REVIEW AND ASSESSMENT
  Acceptance criteria against which review is performed is agreed between the regulator and licensee before the Site evaluation report and is used by the review team.
  The Review basis documents are:
    Regulations on the licensing of Nuclear Installations (PAK/909)
    Regulation on the safety of Siting of Nuclear Installations (PAK/910)
    Regulations on the Safety of Nuclear Power Plants –Quality Assurance(PAK/912)
    NRC Documents (RG 1.70) and other regulatory guides, SRP/NUREG-0800 and 10 CFR Part 100 Site criteria for NPPs
    IAEA Safety Standards, NS-R-3 Site Evaluation for Nuclear Installations with associated guides
    IAEA Safety Standards for Quality Assurance in Siting
    National & International NPP Siting Experience Feedback

## Slide 5: MAJOR DOCUMENTS FOR REVIEW AND ASSESSMENT
  Site Evaluation Report for Site Registration of Nuclear Installation
  Other Documents related to authorization and licensing include:
  Quality Assurance Program applied during site evaluation
  NOCs from Environmental Protection Agency, Water resources, Railway, etc.
  Chapter No. 2 (Site Characteristics) of Safety Analysis Report-SAR (PSAR/FSAR) as per standard format

## Slide 6: REVIEW SCHEDULE & PHASES
  The review of SER typically spreads over a period of six months and normally comprises of following phases:
  SER submission date and docketing
    Phase- 1: Review of Format & Content – RG 1.70
    Phase- 2: Detailed review in the light of Regulations, Regulatory Guides, SRP, Codes & Standards etc.
    Phase- 3: Review in the light of National and International Operating experience feedback (OEF)
  Audit Calculations and Regulatory Inspections
  Some Review deliberations and documentation
6

## Slide 7: OVERSIGHT OF R&A PROCESS
HIGHER MANAGEMENT
ADVISORY COMMITTEE
CORE TEAM
REVIEW TEAM
7

## Slide 8: FORMATION OF REVIEW TEAM
Review Team: Review team comprising of a Lead Reviewer and 6-8 support reviewers keeping in view the relevant disciplines and experience of the review team members.
Core Team: Core team is formed to provide technical support to the review team and to finalize the review queries. The team consists of 3 to 4 senior technical officers.
Advisory Committee/Team: Advisory team consists of senior officers for implementation of effective review strategy and resolution of conflicts, etc.
8

## Slide 9: FLOW CHART FOR REVIEW AND ASSESSMENT
SER received from applicant for Review & Assessment
Cursory Review for docketing of SER
Sent back to the applicant for completion
Detailed Review and Assessment on the basis of documents
Review of responses and preparation of regulatory position
Meeting with applicant for agreements on regulatory position
Distribution of SER for review of format and content and complements
Meeting with core team and review team to finalize the queries
Finalized comments and sent to the NSD for internal approval and comments to Licensee
Preparation of SER (safety evaluation report ) and identification of safety issues
Response from applicant
Comments discussed and evaluated and submitted to Core team
NA
Acceptable

## Slide 10: REVIEW MILESTONES
  Receipt and docketing of the SER based on cursory review
  Review during all phases
  Queries sent to applicant for additional information
  Deadline for receipt of response
  Formulation of regulatory position
  Review meetings (depend upon the review phases)
  Preparation of safety evaluation report and identification of licensing conditions
  Award of authorization for site registration
10

## Slide 11: REVIEW OUTCOME
  Review queries may be raised to address some areas that need additional information:
    Information, analysis deficiencies/ discrepancies in different studies which need to be reassessed, justified and resolved
    Inconsistencies in descriptions presented in various sections of the SER
    Additional analysis in support of some issues identified as a result of review, etc.
  Results/outcome of review is documented in the form of Safety Evaluation Report (SER)
11

## Slide 12: DOCUMENTS GENERATED DURING REVIEW PROCESS
Queries raised by the review team with reference to applicable requirements
Records of communication of review queries to the applicant/licensee
Additional information required as a result of review
Records of internal meetings to review the progress, making position on important issues and final regulatory position
Records of review meetings including commitments of the licensee in the form of Action Sheets signed by the applicant, designer and PNRA
Records of all the directives issued to the licensee
Inspection reports at various stages of authorization including findings and corrective actions taken by the applicant
Results of review and implementation of updated studies as per commitment in review and assessment
Preparation of safety evaluation report SER
12

## Slide 13: ACTION SHEET
Reference No.: NPP-SERQ-XXX | Page X of Y
Regulatory Body Question: | 
Response of Licensee/ Applicant: | 
Position of Regulatory Body: | 
Action(s) to be taken by the Licensee/Applicant: | 
Conclusion: | 
Organization | Regulatory Body | Licensee/Applicant
Reviewer/Expert | (signature with date) | (signature with date)
Team Leader | (signature with date) | (signature with date)

## Slide 14
THANKS